## revised
Tasks
1) Clean up scripts
2) Prepare instructions
3) Prepare sample modeling files for each script
| TASK |  | Hours
dfsu
1 | Calculate Maximum values -> a new dfsu |  | 2
2 | Calculate inundation area -> a single value |  | 2
3 | Convert dfsu to point txt and xyz |  | 2
4 | Concatenate dfsu in time (if model crahsed) |  | 2
5 | Subtract one dfsu from another |  | 2
mesh
1 | Extract xy from an entire mesh |  | 4
2 | Extract xy from an area of a mesh defined by a shp polygon |  | 4
3 | Convert shp polyline to MDF arcs |  | 2
template
1 | Figure templates using MATLAB script |  | 2 | done
Particle Tracking
1 | Create m21fm setup with particle input |  | 4 |  | Total
2 | Post processing xml outputs |  | 6 |  | 32
|  | remaining hours |  |  | 30
32

## initial
Tasks
1) Clean up scripts
2) Prepare instructions
3) Prepare sample modeling files for each script
| TASK | Hours
dfsu
1 | Calculate Maximum values -> a new dfsu | 4
2 | Calculate inundation area -> a single value | 4
3 | Convert dfsu to point txt and xyz | 4
4 | Concatenate dfsu in time (if model crahsed) | 4
5 | Subtract one dfsu from another | 4
mesh
1 | Extract xy from an entire mesh | 4
2 | Extract xy from an area of a mesh defined by a shp polygon | 4
3 | Convert shp polyline to MDF arcs | 2
filter
1 | Godin filter code | 1
template
1 | Figure templates using MATLAB script | 4
Particle Tracking
1 | Create m21fm setup with particle input | 4 | Total
2 | Post processing xml outputs | 6 | 45
Total
| Q/A via email or phone | 20 | 65
65